NEXUSTRADER WEB MIGRATION

Full Parity Implementation Plan

DELIVERABLE 2

Generated: 2026-04-03

# 1. Executive Summary

This plan provides a complete, phased approach to achieve 100% feature parity between the NexusTrader desktop application and the web application. It addresses all gaps identified in the Parity Audit Report (Deliverable 1).

Phase 8 (Critical Foundation): 5 workstreams — Exchange Management, Vault Encryption, AI & ML Settings, Notifications Settings, Remaining Settings Tabs

Phase 9 (Core Trading Pages): 6 workstreams — Notifications Page, Market Regime, Demo Monitor, Tuning Proposals, News & Sentiment, Strategies

Phase 10 (Feature Completion): 7 workstreams — Intelligence upgrades, Orders & Positions upgrades, Backtesting charts, Research Lab, Signal Explorer, Help Center, Manual Trade Entry

Phase 11 (Polish): 5 workstreams — System Health unification, Quant Dashboard, Status Bar, Analytics tabs, Chart enhancements

Total: 23 workstreams across 4 phases. Each workstream specifies backend changes, frontend changes, API endpoints, test requirements, and acceptance criteria.

# 2. Phase Overview

| Phase | Name | Priority | Workstreams | Key Deliverables |
| --- | --- | --- | --- | --- |
| Phase 8 | Critical Foundation | CRITICAL | 5 | Vault Encryption Service, Exchange Management Page, Settings — AI & ML Tab, Settings — Notifications Tab, Settings — Remaining Tabs (Data & Feeds, Backtesting, Intelligence Agents, Portfolio Allocation) |
| Phase 9 | Missing Pages — Core Trading | HIGH | 6 | Notifications Page, Market Regime Page, Demo Live Monitor Page, Tuning Proposals Page, News & Sentiment Page, Strategies Page |
| Phase 10 | Feature Completion & Upgrades | MEDIUM | 7 | Intelligence Page — Meta-Signal & Narrative, Orders & Positions — Advanced Features, Backtesting — Charts & Trade List, Research Lab Page, Signal Explorer Page, Help Center Page, Manual Trade Entry Form |
| Phase 11 | Polish & Parity Completion | LOW | 5 | System Health — Unified Page, Quant Dashboard (Hidden Page), Status Bar, Analytics — Additional Tabs, Chart Enhancements |

# 3. Phase 8 — Critical Foundation

Resolve all CRITICAL gaps. Without these, the web version cannot safely operate as a trading system.

## 8A: Vault Encryption Service

Severity: CRITICAL

Backend Changes:

- Create app/services/vault.py — Fernet AES-256 encryption service

- Implement encrypt(key, value) and decrypt(key) methods

- Store encrypted vault file at data/.nexus_vault.json

- Generate encryption key at first run (data/.nexus_key)

- Add vault key rotation endpoint

- Migrate existing plaintext API keys to vault on first run

Frontend Changes:

- No frontend changes — vault is transparent to the UI

API Endpoints:

- POST /api/v1/vault/rotate-key — Rotate encryption key

- All settings endpoints that handle API keys must encrypt/decrypt via vault

Test Requirements:

- Unit: vault encrypt/decrypt round-trip, key rotation, corruption recovery

- Integration: settings save → vault store → settings load → decrypted correctly

- Security: vault file is not readable as plaintext, key file permissions

Acceptance Criteria:

All API keys stored encrypted. Plaintext keys never written to disk. Vault key rotation works without data loss.

## 8B: Exchange Management Page

Severity: CRITICAL

Backend Changes:

- Create app/api/exchanges.py router

- GET /exchanges — List configured exchanges (id, name, mode, status, last_connected, markets_count)

- POST /exchanges — Add exchange (name, mode, api_key, api_secret, passphrase?) → encrypt via vault

- PUT /exchanges/{id} — Update exchange credentials

- DELETE /exchanges/{id} — Remove exchange

- POST /exchanges/{id}/test — Test connection (connectivity + balance fetch)

- POST /exchanges/{id}/activate — Set as active exchange

- GET /exchanges/supported — List supported exchanges with modes

- Engine command: exchange.list, exchange.add, exchange.update, exchange.delete, exchange.test, exchange.activate

Frontend Changes:

- Create pages/ExchangeManagement.tsx — Full page

- Exchange cards grid (name, mode badge, status, last connected, markets count, actions)

- Add Exchange button → ExchangeDialog modal

- ExchangeDialog: exchange selector (8 exchanges), mode selector (Live/Sandbox/Demo), API key/secret/passphrase form, security note, test connection button with spinner/result

- Edit/Delete/Activate buttons per exchange card

- Add route to sidebar under SYSTEM section

API Endpoints:

- 7 new endpoints as listed above

- All credential fields encrypted via vault service

Test Requirements:

- Backend: CRUD operations, vault integration, connection test mock, supported exchanges list

- E2E: Add exchange → test connection → activate → edit → delete flow

- Security: Credentials never returned in plaintext in API responses (masked)

Acceptance Criteria:

User can add/edit/delete exchanges with 8 exchange types, 3 modes. Credentials encrypted. Connection testing works. Active exchange switchable.

## 8C: Settings — AI & ML Tab

Severity: CRITICAL

Backend Changes:

- Extend settings_api.py — Add AI config fields to settings schema

- Fields: active_provider (auto/anthropic/openai/gemini/ollama), per-provider api_key + model, ml_confidence_threshold, retrain_interval_h, ai_strategy_generation_enabled

- Store API keys via vault encryption

- Engine command: settings.update (with ai.* keys)

Frontend Changes:

- Add 'AI & ML' tab to Settings.tsx

- AI Provider selector (combo/radio group)

- Per-provider: API key input (password mode) + model selector dropdown

- ML confidence threshold slider

- Model retrain interval input

- AI strategy generation toggle

Test Requirements:

- Unit: AI settings save/load, vault encryption for API keys

- E2E: Change provider → enter key → save → reload → verify masked key shown

Acceptance Criteria:

All 4 AI providers configurable. API keys vault-encrypted. Model selection works. Settings persist across restarts.

## 8D: Settings — Notifications Tab

Severity: CRITICAL

Backend Changes:

- Extend settings_api.py — Add notification config fields

- WhatsApp: enabled, twilio_sid, twilio_token, from_number, to_number

- Telegram: enabled, bot_token, chat_id

- Email: enabled, smtp_server, smtp_port, email_address, email_password

- SMS: enabled, twilio_phone, to_phone

- POST /settings/notifications/test/{channel} — Test notification channel

- Store credentials via vault encryption

Frontend Changes:

- Add 'Notifications' tab to Settings.tsx

- 4 channel sections (WhatsApp, Telegram, Email, SMS) each with enable toggle + credential fields + test button

- Test button shows success/error result inline

Test Requirements:

- Unit: notification settings save/load, vault encryption

- Integration: test endpoint sends mock notification (or verifies config validity)

- E2E: Configure channel → test → verify success feedback

Acceptance Criteria:

All 4 notification channels configurable. Credentials vault-encrypted. Test buttons verify connectivity. Settings persist.

## 8E: Settings — Remaining Tabs (Data & Feeds, Backtesting, Intelligence Agents, Portfolio Allocation)

Severity: HIGH

Backend Changes:

- Extend settings_api.py with all remaining desktop settings fields

- Data & Feeds: default_timeframe, historical_days, cache_enabled, sentiment sources (crypto_news, cryptopanic, reddit keys)

- Backtesting: default_fee, default_slippage, default_capital, wf_train_months, wf_validate_months

- Intelligence Agents: per-agent enable/disable (8 agents), FRED/LunarCrush/CoinGlass/CryptoPanic keys

- Portfolio Allocation: btc_weight, eth_weight, alt_weight, auto_rebalance, rebalance_interval, deviation_threshold

Frontend Changes:

- Add 4 new tabs to Settings.tsx (total: 8 tabs matching desktop 7 + API Keys)

- Data & Feeds: timeframe combo, days input, cache toggle, sentiment source toggles + API key fields

- Backtesting: fee/slippage/capital/walk-forward inputs

- Intelligence Agents: 8 agent checkboxes + 4 API key fields

- Portfolio Allocation: weight spinners (sum to 100%), rebalance toggle/interval/threshold

Test Requirements:

- Unit: all settings fields save/load correctly

- E2E: Navigate each tab → modify values → save → reload → verify persistence

Acceptance Criteria:

All 7 desktop Settings tabs replicated in web (split into 8 web tabs for API Keys separation). All values persist. Vault encryption for sensitive keys.

# 4. Phase 9 — Missing Pages — Core Trading

Implement the highest-impact missing pages that support core trading operations.

## 9A: Notifications Page

Severity: HIGH

Backend Changes:

- Create app/api/notifications.py router

- GET /notifications/channels — Channel status (configured, last_sent, error_count per channel)

- GET /notifications/preferences — Current notification preferences (11 toggles + health check interval)

- PUT /notifications/preferences — Update preferences

- POST /notifications/test/{channel} — Test specific channel

- POST /notifications/test-all — Test all configured channels

- GET /notifications/history?limit=50 — Recent notification history

- Engine commands: notification.channels, notification.preferences.get/set, notification.test, notification.history

Frontend Changes:

- Create pages/Notifications.tsx

- 4 channel status cards (WhatsApp/Telegram/Email/SMS) with status dots and last-sent times

- 11 notification preference toggles (trade opened/closed, SL hit, signal rejected, strategy signal, risk warning, market alert, system errors, emergency stop, daily summary, health check) + health check interval dropdown

- Test buttons per channel + Test All button

- Notification history table (time, type, channels, status) with count

- Add to sidebar under SYSTEM section

Test Requirements:

- Backend: preferences CRUD, channel status, test endpoint mocking

- E2E: Toggle preferences → save → test channel → verify history entry

Acceptance Criteria:

Notification preferences configurable. Channel status visible. Test buttons work. History table populated.

## 9B: Market Regime Page

Severity: HIGH

Backend Changes:

- Create app/api/regime.py router

- GET /regime/current — Current regime (name, confidence, classifier_info, description, since_timestamp)

- GET /regime/history?limit=50 — Regime change history

- GET /regime/hmm-probabilities — HMM state probabilities

- GET /regime/statistics — Time-in-regime stats (hours, percentages per regime)

- Engine commands: regime.current, regime.history, regime.hmm, regime.stats

Frontend Changes:

- Create pages/Regime.tsx

- Current Regime card (large dot, name with emoji, confidence %, classifier info, since timestamp)

- Regime Description card (technical details, detection path)

- HMM Probability Distribution (horizontal bar chart for each regime state)

- Regime History table (timestamp, regime, confidence, duration)

- Regime Statistics section (time percentages)

- Add to sidebar under DASHBOARDS section

Test Requirements:

- Backend: all 4 endpoints return correct shapes

- E2E: Page loads → current regime displayed → history populated

Acceptance Criteria:

Current regime visible with confidence. History table shows transitions. HMM probabilities rendered.

## 9C: Demo Live Monitor Page

Severity: HIGH

Backend Changes:

- Create app/api/demo_monitor.py router

- GET /demo/status — Live capital, heat, open positions, win streak, drawdown metrics

- GET /demo/recent-trades — Last 10 trades with P&L

- GET /demo/parity — Live vs Study 4 backtest comparison metrics

- Engine commands: demo.status, demo.trades, demo.parity

Frontend Changes:

- Create pages/DemoMonitor.tsx

- Live metrics cards: capital, heat %, open positions, win streak, max drawdown

- Last 10 trades table (symbol, side, PnL, duration)

- Live vs Backtest comparison panel (WR, PF, Avg R — live vs baseline)

- Auto-refresh every 5s

- Add to sidebar under DASHBOARDS section

Test Requirements:

- Backend: status/trades/parity endpoints

- E2E: Page loads → metrics display → trades table populated

Acceptance Criteria:

Real-time demo health visible. Trade history shows. Backtest comparison renders.

## 9D: Tuning Proposals Page

Severity: HIGH

Backend Changes:

- Create app/api/proposals.py router

- GET /proposals — List proposals (pending/approved/rejected/applied) with filters

- GET /proposals/{id} — Proposal detail (description, evidence, impact, risk)

- POST /proposals/{id}/approve — Approve proposal

- POST /proposals/{id}/reject — Reject proposal

- POST /proposals/{id}/backtest — Run proposal backtest

- GET /proposals/applied-history — Applied change history

- Engine commands: proposals.list, proposals.detail, proposals.approve, proposals.reject, proposals.backtest, proposals.applied

Frontend Changes:

- Create pages/Proposals.tsx

- Summary strip (pending/approved/rejected/applied counts)

- Proposals table (category, parameter, direction, confidence, severity, auto-tune, status) with color coding

- Detail panel: description, evidence, impact, risk, approve/reject buttons, run backtest button

- Applied history table at bottom

- Add to sidebar under ANALYSIS section

Test Requirements:

- Backend: CRUD operations, backtest trigger, status transitions

- E2E: View proposals → approve one → reject one → verify status change

Acceptance Criteria:

Proposals listed with status. Approve/reject workflow works. Backtest-on-demand triggers. Applied history visible.

## 9E: News & Sentiment Page

Severity: HIGH

Backend Changes:

- Create app/api/news.py router

- GET /news/feed?symbol=&sentiment=&timeframe= — News articles (time, source, headline, symbol, sentiment, score)

- GET /news/reddit?symbol=&timeframe= — Reddit posts (time, subreddit, title, score, comments, sentiment)

- GET /news/kpi — Sentiment KPIs (positive/neutral/negative counts + percentages)

- GET /news/history — Sentiment time-series (for chart)

- Engine commands: news.feed, news.reddit, news.kpi, news.history

Frontend Changes:

- Create pages/NewsSentiment.tsx

- Filter bar (symbol, sentiment, timeframe selectors + refresh button)

- KPI strip (3 cards: positive/neutral/negative counts with percentages, color-coded)

- 3-tab layout: News Feed table (clickable rows → open article), Reddit table, History chart (sentiment over time)

- Add to sidebar under RESEARCH section

Test Requirements:

- Backend: feed/reddit/kpi/history endpoints with filters

- E2E: Page loads → KPIs display → news table populated → filter works

Acceptance Criteria:

News feed displays articles with sentiment. Reddit tab shows posts. KPI strip accurate. History chart renders.

## 9F: Strategies Page

Severity: HIGH

Backend Changes:

- Create app/api/strategies.py router

- GET /strategies — Model grid (name, type, enabled, weight, WR, PF, trades, P&L)

- GET /strategies/{model}/parameters — Per-model parameters with current values and defaults

- PUT /strategies/{model}/parameters — Update model parameters

- GET /strategies/{model}/regime-affinity — Per-regime affinity values (-1 to +1)

- PUT /strategies/{model}/regime-affinity — Update affinity values

- GET /strategies/global-parameters — Cross-model global settings

- PUT /strategies/global-parameters — Update global settings

- GET /strategies/audit-log — Change history

- Engine commands: strategies.list, strategies.params.get/set, strategies.affinity.get/set, strategies.global.get/set, strategies.audit

Frontend Changes:

- Create pages/Strategies.tsx

- Model grid table (sortable, color-coded by type: CORE/AGENT/ML/META)

- 4-tab detail panel: Parameters (form per model), Regime Affinity (sliders), Global Parameters, Audit Log (text log)

- Dirty tracking with save/reset buttons

- Add to sidebar under SYSTEM section (or accessible via nav)

Test Requirements:

- Backend: CRUD for model params, affinity, global params, audit log

- E2E: Select model → edit param → save → verify persisted → check audit log entry

Acceptance Criteria:

All models listed. Parameters editable per-model. Regime affinity adjustable. Global params configurable. Audit log tracks changes.

# 5. Phase 10 — Feature Completion & Upgrades

Upgrade PARTIAL features to full parity, implement medium-priority missing pages.

## 10A: Intelligence Page — Meta-Signal & Narrative

Severity: MEDIUM

Backend Changes:

- Extend signals.py — GET /signals/meta-signal (verdict, numeric value, confidence, bias, macro risk, veto status)

- GET /signals/narrative (bullish_drivers[], bearish_drivers[], contradictory[])

- GET /signals/risk-conditions (macro_veto, high_risk, risk_off_bias warnings)

Frontend Changes:

- Add Meta-Signal Summary Bar to Intelligence.tsx (verdict, signal value, confidence, bias, macro risk, veto badge)

- Add Bullish/Bearish Narrative section (weighted driver breakdown)

- Add Active Risk Conditions section

- Enhance agent cards with weight display and centered progress bars

Test Requirements:

- Backend: meta-signal/narrative/risk-conditions endpoints

- E2E: Meta signal bar displays → narrative section renders → risk conditions visible

Acceptance Criteria:

Meta-signal summary bar matches desktop. Narrative analysis shows driver breakdown. Risk conditions surfaced.

## 10B: Orders & Positions — Advanced Features

Severity: MEDIUM

Backend Changes:

- Extend trades.py — GET /trades/history with advanced filters (side, regime, exit_reason, min_score)

- GET /trades/summary — Summary strip KPIs (open count, total PnL, WR, avg holding, best/worst)

- GET /trades/{id}/analysis — IDSS analysis detail (classification, scores, R:R, regime affinity, AI explanation)

Frontend Changes:

- Add filter bar to Trading.tsx (symbol, side, regime, exit reason, min score)

- Add summary strip (6 KPIs) above tabs

- Add IDSS Analysis detail panel below trade history (expandable on row click)

Test Requirements:

- Backend: advanced filter combinations, summary calculation, analysis detail

- E2E: Apply filters → verify results → click trade → see analysis detail

Acceptance Criteria:

Advanced filters work. Summary strip shows KPIs. IDSS analysis detail renders for selected trades.

## 10C: Backtesting — Charts & Trade List

Severity: MEDIUM

Backend Changes:

- Extend backtest.py — GET /backtest/results/{id}/equity-curve (for chart data)

- GET /backtest/results/{id}/trades (individual backtest trades)

Frontend Changes:

- Add equity curve chart to Backtest.tsx results section (lightweight-charts area series)

- Add drawdown chart below equity curve

- Add trade-by-trade table (expandable/collapsible) with sortable columns

Test Requirements:

- Backend: equity curve and trades data shape

- E2E: Run backtest → results show charts + trade table

Acceptance Criteria:

Equity curve and drawdown charts render. Trade-by-trade list shows individual trades with sort.

## 10D: Research Lab Page

Severity: MEDIUM

Backend Changes:

- Create app/api/research.py router

- POST /research/baseline — Run baseline backtest

- GET /research/baseline — Get cached baseline result

- POST /research/sweep — Launch parameter sweep (config: strategy, symbols, dates, objective, worker count)

- GET /research/sweep/{id}/status — Sweep progress (trial count, best PF, elapsed)

- GET /research/sweep/{id}/results — Full sweep results (trial-by-trial)

- GET /research/parameters — Available parameters with FIXED/OPTIMIZE toggle + ranges

Frontend Changes:

- Create pages/ResearchLab.tsx

- Baseline panel (status, metrics, run/cache buttons)

- Parameter panel (FIXED/OPTIMIZE toggles per param, min/max range inputs)

- Search panel (strategy, symbols, dates, objective, workers, cost, mode)

- Progress panel (trial counter, best PF, progress bar, leaderboard preview)

- Results table (sortable, filterable trial results)

- Add to sidebar under RESEARCH section

Test Requirements:

- Backend: baseline/sweep lifecycle, results storage

- E2E: Run baseline → configure sweep → launch → monitor progress → view results

Acceptance Criteria:

Baseline runs and caches. Sweep launches with progress tracking. Results table shows trial data.

## 10E: Signal Explorer Page

Severity: MEDIUM

Backend Changes:

- Create app/api/signal_explorer.py router

- GET /signal-explorer?symbol=&strategy=&direction=&days=&page=&per_page= — Paginated signals

- GET /signal-explorer/{id} — Signal detail (meta, IDSS data, rationale)

Frontend Changes:

- Create pages/SignalExplorer.tsx

- Filter bar (symbol, strategy, direction, date range)

- Paginated signal table (time, symbol, strategy, direction, strength, entry, regime)

- Detail panel (signal meta, IDSS data, entry/SL/TP, rationale text)

- Accessible via internal navigation

Test Requirements:

- Backend: filter combinations, pagination, detail

- E2E: Load signals → apply filter → paginate → view detail

Acceptance Criteria:

Signal history browsable with filters. Pagination works. Detail panel shows full signal data.

## 10F: Help Center Page

Severity: MEDIUM

Backend Changes:

- No backend needed — articles can be bundled as static content or fetched from docs/

Frontend Changes:

- Create pages/HelpCenter.tsx

- Search bar with real-time filtering

- Category sidebar (Getting Started, Trading, Risk, Intelligence, Regime, Backtesting)

- Article reader (markdown → HTML rendering)

- Onboarding checklist (6 items with completion tracking via localStorage)

Test Requirements:

- E2E: Search articles → navigate categories → read article → checklist interaction

Acceptance Criteria:

Articles searchable and readable. Categories filter correctly. Onboarding checklist tracks progress.

## 10G: Manual Trade Entry Form

Severity: MEDIUM

Backend Changes:

- POST /trading/manual-entry — Submit manual paper trade (symbol, side, size, entry_price, sl, tp)

Frontend Changes:

- Add manual trade entry form to Trading.tsx (modal or collapsible panel)

- Fields: symbol selector, side (long/short), size USDT, entry price, stop loss, take profit

- Submit button with confirmation

Test Requirements:

- Backend: manual entry validation, position creation

- E2E: Open form → enter trade → submit → verify position appears

Acceptance Criteria:

Manual paper trades can be entered. Position appears in open positions. Standard close/management works.

# 6. Phase 11 — Polish & Parity Completion

Complete remaining LOW-priority items for full feature parity.

## 11A: System Health — Unified Page

Severity: LOW

Backend Changes:

- Extend system.py health endpoint with notification channel status, agent stale/error detail, per-exchange latency/symbol count

Frontend Changes:

- Create pages/SystemHealth.tsx — unified view with crash status, exchange cards, agent grid, DB section, notification channels, event log

- Move relevant data from Validation.tsx to unified health page

Test Requirements:

- E2E: Page shows all subsystem statuses in one view

Acceptance Criteria:

Unified system health page matching desktop layout.

## 11B: Quant Dashboard (Hidden Page)

Severity: LOW

Backend Changes:

- Extend dashboard endpoints with ticker strip data, account summary

Frontend Changes:

- Create pages/QuantDashboard.tsx — ticker strip (live prices), candlestick chart, performance summary, live positions, crash risk, account summary

- Hidden route accessible via internal navigation

Test Requirements:

- E2E: Page loads with live data

Acceptance Criteria:

Quant dashboard renders with live price updates and account summary.

## 11C: Status Bar

Severity: LOW

Backend Changes:

- No changes needed — data already available from health endpoint

Frontend Changes:

- Add persistent status bar to Layout.tsx (UTC clock, exchange name/status, feed status, AI provider name)

- Auto-refresh every 5s

Test Requirements:

- E2E: Status bar visible on all pages, updates in real-time

Acceptance Criteria:

Status bar matches desktop: UTC clock, exchange, feed, AI indicators.

## 11D: Analytics — Additional Tabs

Severity: LOW

Backend Changes:

- Add edge analysis endpoints

- Add trade quality scoring endpoints

Frontend Changes:

- Add Edge Analysis tab to Analytics.tsx

- Add additional quality metrics matching desktop's 9-tab layout

Test Requirements:

- E2E: Additional analytics tabs render with data

Acceptance Criteria:

Analytics matches desktop's 9 tabs.

## 11E: Chart Enhancements

Severity: LOW

Backend Changes:

- No changes needed

Frontend Changes:

- Add more indicator overlays (EMA50, Bollinger Bands, VWAP)

- Improve signal marker styling

Test Requirements:

- E2E: Indicators toggle and render correctly

Acceptance Criteria:

Chart indicators match desktop's pyqtgraph capabilities.

# 7. Security Considerations

All phases must adhere to the following security requirements:

Credential Storage:

- All API keys, secrets, tokens, and passwords MUST be encrypted via the Vault service (Phase 8A) before storage.

- No plaintext credentials in config files, database records, or API responses.

- API responses that include key fields must return masked values (e.g., ****last4).

Exchange Credentials:

- Exchange API keys encrypted at rest. Decrypted only in-memory for connection testing and trading.

- Connection test worker runs in background thread with timeout.

- Passphrase field only shown for exchanges that require it (KuCoin, OKX).

Notification Credentials:

- Twilio SID/token, SMTP password, Telegram bot token — all vault-encrypted.

- Test endpoints must not leak credentials in error messages.

# 8. Testing Strategy

Each workstream specifies its own test requirements. In addition, the following cross-cutting tests apply:

Unit Tests (per workstream):

- All new API endpoints with mocked engine commands

- Vault encryption round-trip for all credential fields

- Input validation (min/max ranges, required fields, type checking)

Integration Tests:

- Engine command round-trip (API → Redis queue → engine → response)

- Settings save → engine reload → verify runtime config changed

E2E Tests (Playwright):

- One spec file per new page (login → navigate → interact → verify)

- Responsive tests for all new pages (375px mobile + 1280px desktop)

Regression:

- Full backend test suite must pass after each phase (target: 0 failures)

- All existing E2E specs must continue passing

# 9. Conclusion

This plan covers 23 workstreams across 4 phases to achieve 100% feature parity. Phase 8 (Critical) must be completed first as it provides the security foundation (vault encryption) and the most-blocking feature (exchange management). Phases 9-11 can be executed in order of priority.

No implementation will begin until this plan is approved by the user.