NexusTrader Web Migration

Phase 6 — System Hardening & Production Readiness

Design & Implementation Plan

FOR APPROVAL — NO IMPLEMENTATION UNTIL APPROVED

Date: April 3, 2026

Status: AWAITING APPROVAL

Phase 7 (Final Validation) follows this phase

# 1. Scope Overview

Phase 6 hardens the web application for production deployment. It addresses 28 specific gaps identified during the Phase 5 audit across backend security, frontend resilience, WebSocket stability, and test coverage. Phase 7 (Final Validation) follows and proves the system end-to-end.

The scope is organized into 6 workstreams, each with discrete deliverables and acceptance criteria:

| WS | Workstream | Scope Summary |
| --- | --- | --- |
| 6A | Backend Error Handling & Logging | Global exception handler, structured JSON logging, request audit middleware, silent-error elimination |
| 6B | Config & Auth Hardening | Startup validation (JWT secret, DB, encryption key), account lockout, password complexity, setup endpoint idempotency |
| 6C | WebSocket Hardening | Per-client message rate limiting, message size cap, cryptographic connection IDs, subscribe error responses |
| 6D | Frontend Resilience | React error boundary, API client timeout+retry, loading skeletons for Dashboard/Trading/Scanner, 404 page |
| 6E | E2E Test Expansion | 4 new spec files (setup, charts, intelligence, risk), fix brittle selectors, add CI caching+retry+docker-logs |
| 6F | Backtest Stress Expansion | Large dataset test (5yr/3 symbols), concurrent cancellation, memory baseline, timeout cascade |

Explicitly OUT OF SCOPE for Phase 6 (deferred to Phase 7 or post-launch):

- Multi-user role-based access control (single admin user is sufficient for production)

- Horizontal scaling / distributed rate limiting (single-instance deployment)

- Mobile touch gesture testing (swipe, pinch — not needed for trading dashboard)

- Charts accessibility fallback (lightweight-charts is visual-only by design)

- HTTP-only cookie auth migration (current Bearer token pattern is standard for SPAs)

# 2. Workstream 6A — Backend Error Handling & Logging

## 2.1 Global Exception Handler

Add a global @app.exception_handler(Exception) in main.py that catches all unhandled exceptions and returns a sanitized JSON response. In production (NEXUS_DEBUG=false), stack traces are suppressed. In debug mode, the full traceback is included.

File: web/backend/main.py

- Add exception_handler for Exception → returns {"detail": "Internal server error", "request_id": "..."} with 500 status

- Add exception_handler for RequestValidationError → returns normalized 422 with field-level errors

- Generate request_id (UUID4) per request via middleware, attach to response headers as X-Request-ID

## 2.2 Structured JSON Logging

Replace plain-text logging with structured JSON format for all log output. This enables log aggregation, filtering, and alerting in production.

File: web/backend/app/logging_config.py (new)

- JSON formatter: {"timestamp", "level", "logger", "message", "request_id", "extra"}

- Sensitive data filter: mask JWT tokens, passwords, API keys in log output

- Configurable log level via NEXUS_LOG_LEVEL env var (default: INFO)

## 2.3 Request Audit Middleware

Add middleware that logs every HTTP request with method, path, status code, latency, and authenticated user_id (if present).

File: web/backend/app/middleware/audit.py (new)

- Logs: {method, path, status, latency_ms, user_id, request_id, client_ip}

- Excludes /health and /health/ready from audit logs (high-frequency healthcheck noise)

## 2.4 Silent Error Elimination

Fix 4 identified bare except clauses in ws/manager.py that swallow errors without logging:

- Line ~203: dead.append(conn_id) → add logger.warning with conn_id and error

- Line ~215: self.disconnect(conn_id) → add logger.warning

- Line ~224: pass → add logger.debug for expected close errors

- Replace all except Exception with specific exception types where possible

# 3. Workstream 6B — Config & Auth Hardening

## 3.1 Startup Configuration Validation

Add a validate_production_config() function that runs at startup when NEXUS_DEBUG=false:

File: web/backend/app/config.py

- FAIL startup if NEXUS_JWT_SECRET == default placeholder or length < 32 chars

- FAIL startup if NEXUS_ENCRYPTION_KEY is empty

- WARN if CORS origins contain http:// (non-HTTPS) in production

- WARN if database URL contains default password (nexus:nexus)

- Log all validated settings at INFO level (with secrets masked)

## 3.2 Account Lockout

Add progressive lockout after failed login attempts:

File: web/backend/app/api/auth.py

- Track failed_login_attempts and locked_until on User model

- After 5 consecutive failures: lock account for 15 minutes

- After 10 consecutive failures: lock account for 1 hour

- Successful login resets the counter

- Locked accounts return 423 with retry_after header

## 3.3 Password Complexity

Add validation on /auth/setup and any future password-change endpoints:

- Minimum 8 characters

- At least 1 uppercase, 1 lowercase, 1 digit

- Return 422 with specific validation error if requirements not met

## 3.4 Setup Endpoint Hardening

The /auth/setup endpoint currently only checks if any user exists. Harden:

- Return 409 if any user already exists (current behavior — verify)

- Add rate limit: 3 req/min (prevent brute-force account creation)

- Log setup attempts at WARNING level (security audit trail)

# 4. Workstream 6C — WebSocket Hardening

## 4.1 Per-Client Message Rate Limiting

Prevent clients from flooding the server with rapid messages:

File: web/backend/app/ws/manager.py

- Add sliding-window rate limiter: 20 messages/second per connection

- Exceeding limit: send {"type": "error", "message": "rate_limited"} and ignore message

- 3 consecutive rate-limit violations: close connection with code 1008 (Policy Violation)

## 4.2 Message Size Cap

- Maximum incoming message size: 4 KB (subscribe/unsubscribe/ping/pong are all <1 KB)

- Oversized messages: close connection with code 1009 (Message Too Big)

## 4.3 Cryptographic Connection IDs

Replace id()-based connection IDs with UUID4:

- Current: f"ws_{user_sub}_{id(websocket)}" → uses Python object ID (predictable, reusable)

- New: f"ws_{user_sub}_{uuid4().hex[:12]}" → cryptographically random, non-reusable

## 4.4 Subscribe Error Responses

- Invalid channel subscription now returns {"type": "error", "action": "subscribe", "channel": "...", "message": "invalid_channel"}

- Currently: silent failure (client subscribes to non-existent channel, gets no data)

# 5. Workstream 6D — Frontend Resilience

## 5.1 React Error Boundary

Wrap the application shell in an error boundary that catches uncaught component errors and renders a recovery UI instead of crashing the entire app.

Files:

- web/frontend/src/components/ErrorBoundary.tsx (new) — class component with componentDidCatch

- web/frontend/src/App.tsx — wrap AppShell routes in <ErrorBoundary>

- Recovery UI: "Something went wrong" message with a "Reload page" button

- Error logged to console.error with component stack (production: structured logging when available)

## 5.2 API Client Hardening

Add timeout, retry, and error normalization to the centralized axios client:

File: web/frontend/src/api/client.ts

- Add 15-second request timeout (currently: no timeout → hangs indefinitely)

- Add retry for 5xx and network errors: 2 retries with exponential backoff (1s, 2s)

- Normalize error responses into {status, message, requestId} shape

- Do NOT retry 4xx errors (client errors are intentional)

## 5.3 Loading Skeletons

Add shimmer/skeleton placeholders for the 3 highest-traffic pages to eliminate blank-flash on data load:

- Dashboard: 4 metric card skeletons + trade list skeleton

- Trading: positions table skeleton + history table skeleton

- Scanner: candidate card skeletons

Implementation: Tailwind animate-pulse divs matching the real layout dimensions.

## 5.4 404 Page

Replace the silent catch-all redirect with a proper 404 page:

- web/frontend/src/pages/NotFound.tsx (new) — "Page not found" with link to Dashboard

- Update App.tsx: path="*" → element={<NotFound />} instead of Navigate

# 6. Workstream 6E — E2E Test Expansion

## 6.1 New Spec Files (4)

| Spec File | Tests | Coverage |
| --- | --- | --- |
| 11-setup.spec.ts | 3 | First-run setup flow: render form, create admin account, redirect to dashboard after setup |
| 12-charts.spec.ts | 2 | Navigate to charts page (lazy-loaded), verify chart container renders, symbol selector visible |
| 13-intelligence.spec.ts | 2 | Navigate to intelligence page, verify agent status cards render, confluence section visible |
| 14-risk.spec.ts | 2 | Navigate to risk page, verify portfolio heat metric, crash defense status, kill switch button present |

## 6.2 Brittle Selector Fixes

Replace 7 identified .first() calls on generic elements with scoped, resilient selectors:

- Scope all selectors to page.locator('main') to avoid sidebar duplicates

- Use getByRole() with name matchers instead of getByText().first()

- Add data-testid attributes to ambiguous elements where needed

## 6.3 CI Pipeline Improvements

File: web/.github/workflows/e2e.yml

- Add npm cache: actions/setup-node@v4 with cache: npm (saves ~60s per run)

- Change Playwright retries to 2 in CI (from 1) for flake resilience

- Add docker compose logs collection on failure (upload as artifact)

- Add engine healthcheck to docker-compose.e2e.yml

# 7. Workstream 6F — Backtest Stress Expansion

Add 4 new stress test scenarios to test_backtest_stress.py:

| # | Scenario | What It Tests | Pass Criteria |
| --- | --- | --- | --- |
| 1 | Large dataset (5yr, 3 symbols) | Memory and CPU pressure under realistic load | Completes without OOM; result contains all 3 symbols |
| 2 | Concurrent cancellation | 3 simultaneous cancel requests on same job | No crash; status transitions cleanly to cancelled |
| 3 | Memory baseline | Run 5 sequential backtests, check no memory leak | RSS delta < 50 MB across 5 runs |
| 4 | Timeout cascade | Start backtest, let client timeout, retry immediately | Second request succeeds; first job cleaned up |

# 8. Test Plan

## 8.1 Unit Tests (new)

| # | Test File | Count (est) | Coverage |
| --- | --- | --- | --- |
| 1 | test_phase6_error_handling.py | ~12 | Global exception handler, validation errors, request ID generation |
| 2 | test_phase6_logging.py | ~8 | JSON formatter, sensitive data masking, log level config |
| 3 | test_phase6_config_validation.py | ~10 | Startup checks: JWT, encryption key, CORS, DB URL |
| 4 | test_phase6_auth_hardening.py | ~12 | Account lockout, password complexity, setup idempotency |
| 5 | test_phase6_ws_hardening.py | ~10 | Message rate limit, size cap, connection ID, subscribe errors |

Estimated new unit tests: ~52

## 8.2 Sandbox Integration Tests

- Audit middleware + logging: verify request audit logs contain expected fields (fakeredis)

- WebSocket rate limiting: simulate rapid messages via in-process WS manager

## 8.3 Docker Integration Tests

- Config validation: startup failure with bad JWT secret against real PostgreSQL

- Account lockout persistence: lock/unlock survives API restart (state in DB)

## 8.4 E2E Browser Tests

- 4 new spec files (Section 6.1): 9 new test cases × 2 viewports = 18 new test runs

- Existing 46 tests re-run after all changes to confirm no regression

- Total E2E target: 55 test runs (27 tests × 2 viewports + 1 setup-only)

## 8.5 Test Taxonomy Compliance

All new tests follow the established taxonomy:

- Pure unit tests: no marker needed (default)

- Sandbox integration: @pytest.mark.sandbox_integration

- Docker integration: @pytest.mark.docker_integration (auto-skipped without DB)

- pytest tests/ must remain clean green (0 failures, N skipped for docker_integration)

# 9. Mobile + Desktop Validation Plan

All E2E specs run on both desktop-chromium (1280x720) and mobile-chromium (Pixel 5, 393x851). The new specs will verify:

- Setup page: form renders correctly on both viewports

- Charts: lazy-loaded container renders (chart library may not render in headless — test container only)

- Intelligence: agent cards stack vertically on mobile (grid-cols-1)

- Risk: kill switch button is accessible on mobile (touch target size)

- Error boundary: recovery UI renders on both viewports

- 404 page: renders correctly on both viewports

Existing 10-mobile.spec.ts already validates hamburger menu and horizontal overflow. No changes needed.

# 10. Performance Optimization Targets

Phase 6 establishes baselines rather than optimizing for specific targets. No performance regressions are expected from hardening changes.

| Metric | Baseline (establish) | Regression Threshold |
| --- | --- | --- |
| API /health response time | Measure current | Must stay < 500ms |
| API /dashboard/summary response time | Measure current | Must stay < 2s |
| Frontend bundle size (gzip) | Measure current | Must not increase > 10% |
| Playwright E2E suite duration | Measure current | Must stay < 5 minutes |
| Backend test suite duration | ~4 seconds (current) | Must stay < 10 seconds |

Baseline measurements will be recorded in the Phase 6 Gate Report.

# 11. Acceptance Criteria

Each criterion must be demonstrated with specific evidence in the Gate Report:

| # | Criterion | Required Evidence |
| --- | --- | --- |
| 1 | Global 500 handler returns sanitized JSON (no stack trace in prod) | Unit test: mock exception → verify response JSON has no traceback |
| 2 | Structured JSON logging with sensitive data masking | Unit test: log with JWT token → verify token is masked in output |
| 3 | Request audit middleware logs method/path/status/latency | Unit test: send request → verify audit log entry |
| 4 | Startup fails if JWT secret is placeholder | Unit test: set default secret + NEXUS_DEBUG=false → SystemExit |
| 5 | Account lockout after 5 failed logins | Unit test: 5 bad passwords → 6th returns 423 with retry_after |
| 6 | Password complexity enforced (8+ chars, upper/lower/digit) | Unit test: weak password → 422 with validation error |
| 7 | WS message rate limit (20/sec) enforced | Unit test: 25 rapid messages → last 5 get rate_limited error |
| 8 | WS message size cap (4 KB) enforced | Unit test: 5 KB message → connection closed with 1009 |
| 9 | WS connection IDs are UUID-based (not id()) | Unit test: 2 connections → IDs match UUID pattern |
| 10 | React error boundary catches component crash | E2E test: force error → recovery UI renders |
| 11 | API client has 15s timeout and 5xx retry | Manual test or unit test of axios interceptor config |
| 12 | Loading skeletons on Dashboard/Trading/Scanner | E2E screenshot or visual verification |
| 13 | 404 page renders for unknown routes | E2E test: navigate to /nonexistent → see 404 page |
| 14 | 4 new E2E specs pass on both viewports | Playwright report showing 55+ test runs passed |
| 15 | Brittle selectors fixed (no .first() on unscoped) | Code diff: all .first() calls scoped to main or removed |
| 16 | CI pipeline has caching + retry + docker-logs | e2e.yml diff showing cache, retries: 2, log collection |
| 17 | 4 new backtest stress scenarios pass | pytest output showing all stress tests green |
| 18 | Backend test suite: 0 failures (docker_integration skipped) | pytest output: N passed, 4 skipped |
| 19 | No silent except clauses in WS manager | Code diff: all bare except replaced with logging |
| 20 | Performance baselines recorded (no regression) | Table of measured values in Gate Report |

# 12. Files Changed (Estimated)

## 12.1 Backend (modified)

- web/backend/main.py — global exception handlers, audit middleware registration

- web/backend/app/config.py — startup validation, env var checks

- web/backend/app/api/auth.py — account lockout, password complexity

- web/backend/app/ws/manager.py — rate limit, size cap, connection ID, subscribe errors, silent-error fixes

- web/backend/app/ws/routes.py — rate limit enforcement in message loop

## 12.2 Backend (new)

- web/backend/app/logging_config.py — structured JSON logging

- web/backend/app/middleware/audit.py — request audit middleware

- web/backend/tests/test_phase6_error_handling.py

- web/backend/tests/test_phase6_logging.py

- web/backend/tests/test_phase6_config_validation.py

- web/backend/tests/test_phase6_auth_hardening.py

- web/backend/tests/test_phase6_ws_hardening.py

## 12.3 Frontend (modified)

- web/frontend/src/App.tsx — error boundary wrapper, 404 route

- web/frontend/src/api/client.ts — timeout, retry, error normalization

- web/frontend/src/pages/Dashboard.tsx — loading skeleton

- web/frontend/src/pages/Trading.tsx — loading skeleton

- web/frontend/src/pages/Scanner.tsx — loading skeleton

## 12.4 Frontend (new)

- web/frontend/src/components/ErrorBoundary.tsx

- web/frontend/src/components/Skeleton.tsx — reusable skeleton primitives

- web/frontend/src/pages/NotFound.tsx

## 12.5 E2E Tests (new)

- web/frontend/e2e/11-setup.spec.ts

- web/frontend/e2e/12-charts.spec.ts

- web/frontend/e2e/13-intelligence.spec.ts

- web/frontend/e2e/14-risk.spec.ts

## 12.6 Infrastructure (modified)

- web/.github/workflows/e2e.yml — caching, retry, docker-logs

- web/docker-compose.e2e.yml — engine healthcheck

- web/backend/tests/test_backtest_stress.py — 4 new scenarios

# 13. Execution Order

Strict sequential execution. Each workstream completes with tests before the next starts.

- 6A: Backend Error Handling & Logging (foundation for all subsequent work)

- 6B: Config & Auth Hardening (depends on logging for audit trail)

- 6C: WebSocket Hardening (depends on logging for rate-limit diagnostics)

- 6D: Frontend Resilience (independent but uses hardened backend)

- 6E: E2E Test Expansion (validates all prior workstreams)

- 6F: Backtest Stress Expansion (independent, runs last)

- Gate: Phase 6 Gate Report with all 20 acceptance criteria evidence

# 14. Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Account lockout changes DB schema | Requires Alembic migration | Add migration in 6B; test with docker_integration marker |
| Structured logging breaks existing log parsing | Monitoring disruption | Feature-flag: NEXUS_LOG_FORMAT=json¦text (default text in dev) |
| Error boundary masks real errors in dev | Harder to debug | Only catch in production; in dev, let errors propagate |
| New E2E specs may be flaky in CI | CI instability | CI retries: 2; scoped selectors; explicit waits |
| Message rate limiting too aggressive | Legitimate WS messages dropped | 20/sec is 10x normal usage; configurable via env var |

# 15. Deferred to Phase 7 (Final Validation)

Phase 7 proves the system. It does not add features. Scope:

- Full end-to-end validation across all test tiers (unit + sandbox + docker + E2E browser)

- Production deployment validation: Docker stack + Cloudflare Access + Tunnel + public URL

- Security verification: auth flows, headers, access control against real infrastructure

- Final mobile + desktop UX validation with screenshots

- Architecture, deployment, and runbook documentation

- Final Completion Report with explicit READY / NOT READY verdict